## Sheet1
In General, Consider: |  |  | For major retrofits: what other components peripherals will be needed?
Extra equipment / components / materials
For major retrofits: what other components peripherals will be needed?
Refer to a design for the system to be installed, and go through all components: piping, valves
Safety systems
Fire alarms?
Extra labor or labor $
Permits / regulations
Customer risks / needs
Maintenance / ongoing costs
Maintenace activities needed, like clean-out of dirty condenser water systems,
and how is responsibility and contingency for this established
Create a list of all components
Engineering review
Contractor review
Ask questions:
What could go wrong?
Will we need any more retrofits?
Has all work been accounted for?
EXAMPLE: chiller set-up and piping (valves, piping layout)
Establish intent:
Document how systems will save energy – controls etc.
For each ECO, consider whether it will require:
Clean-up
Structural work
Enclosure
What will be installed outdoors? (weatherproof components)
Supports / hangers
Insulation
Demolition and / or rebuilding
Access
Overtime install, start-up, or some part of the work
Interruption to customer systems
Union labor
In-house labor
SOMBWA (small, neighborhood, women owned, minority owned)
For each ECO, consider whether it will require:
Storage
Shipping
Rigging and structural
Controls
Wiring
Plumbing
Anything custom-made (motors for example)
Any “ripple effects” resulting from increasing the size or capacity of equipment (what else needs to be up-sized)
Repairs to existing systems required
Equipment not in use or out of order
For each ECO, consider:
Permits / air quality issues
Hazardous materials needed for retrofit or systems (glycol)
Other environmental hazards (asbestos, for example)
Neighborhood approval (big one for cogen)
Increase in electric service (tough one in NYC)
Existing contracts or obligations to buy energy
Increase in gas service or gas pressure (can be an issue for cogen)
Maintenance contracts to keep stuff running (cogen and absorption cooling)
Commissioning, M&V and other work required well after the fact
For each ECO, consider financial obligations:
Channel partner obligations
Contingency
Bonding for subs
Bonding for Bluestone
In general, extra $ for any of the things on this list
Will the customer need financing?
Verify equipment is specified for conditions:
Exposed to the weather or other harsh environments?
Motors: TEFC, wash-down duty or explosion proof
Specific set-ups: what configuration should it be set up in?
Other more general risk factors:
Tough customer
Customer contract - see if you can look at this AHEAD of time…
Tough utility or M&V requirements
Limited choice of contractor / tough contractor
Others might steal the job
Customer may self-perform
Occupant complaints
Reliability
New / untested technology
Lack of utility rebate and/or support for the ECM or technology
Existing trouble in the facility
Specific things to make sure of for controls
1. Graphical user interface – the VAV / t-Stats needs to be shown on a floor plan / map, with the person’s name / meeting room info as reference.
2. We need to clarify if customer (and vendor) wants to use tablets to access the system, TRIDIUM V4. Does not have RIGHT CLICK function available on ANDROID nor APPLE tablets. Extra work needs to be done to enable those.
3. Notifications – email and / or text messages. Whats infrastructure (email server info, email account, phone line for texting? Email to text service). Need to clarify.
4. Need know from customer how and what they would like to have alarmed.
5. For conversion to DDC, the T-stats we are replacing from old ddc or pneumatics, we should specify t-stats with digital temp display and programmable to allow limited temp adjustment range as an “upgraded option”.
6. Need to specify tredning data requirements. For example. Show space temp, setpoings, and OA temp, on one screen, and how frequenly the data should be pulled.
7. DEFINITELY, need to have the vendor do therir own CX before turing the system over to us for review.